## Cover
Equipment List
UWA ELEC5550
ELEC5550 - Project Risk Register
Project Name |  | 2-Way Free-Space Optical Communication System
Team Identifier |  | Team 0-26
Student Name |  | Student Number | Role
Jonathan Chivers |  | 23247451 | Quality Assurance
Varen Lutchmanen |  | 23024474 | Project Manager
Tom McAndrew |  | 22710651 | Project Manager
Hannah McLean |  | 22715312 | Client Liason
James Plummer |  | 23093628 | Project Administrator
Sumil Saju |  | 24573872 | Configuration Manager
Project Partners |  | Dilusha Silva, Michal Zewarta
Supervisor |  | Osaka Rubasinghe
Group Meeting Time |  | Thursday 4pm (Stream 2)
Date | Version | Description | Author | QA Review
2025-08-04 | 0.0 | Initial Draft | James Plummer | N/A
2025-08-05 | 1.0 | Added Cover Sheet & Revision History | Jonathan Chivers | N/A
? | 1.1 | Populated Risks Weekly | James Plummer | N/A
2025-08-28 | 1.2 | Added Residual Risk Columns | Jonathan Chivers | N/A

## Risk Register
PROJECT RISK REGISTER
A risk is any factor, event or influence that threatens the successful completion of the project.
RISK DESCRIPTION (Adjust sub headings to suit your project) |  | POTENTIAL IMPACT | RISK ASSESSMENT |  |  | RISK TREATMENT / MITIGATION | RESIDUAL RISK |  |  | RESPONSIBILITY
|  |  | Consequence | Likelihood | Risk Rating- from risk matrix |  | Residual Consequence | Residual Likelihood | Residual Risk Rating
NO. | Project Scope
1 | Initial scope provided is unclear in a number of areas. | Project delivered varies significantly from what the client wanted. | Major | Likely | Extreme | Clarify scope through TQ's if not clearly stated in project brief. |  |  |  | Client Liason Manager
2 | Scope creep due to unclear or evolving requirements from project partner. | Additional requirements/problems that arise whilst delivering project. | Moderate | Possible | High | Regular requirement reviews with client and change control process. These will be answered through TQs |  |  |  | Client Liason Manager
Project Quality
3 | Final PCB design not meeting performance requirements (latency, transfer rate). | System may fail demonstration or not meet partner expectations. | Major | Possible | High | Early prototype testing and performance validation. |  |  |  | Quality Assurance Manager
4 | Limited MCU Tx Rx Speed | Data throughput bottleneck affects communication reliability. | Moderate | Likely | High | Optimise firmware, consider alternative MCU if needed. |  |  |  | Quality Assurance Manager
Project Schedule
5 | Not having equipment on time | Delays in testing and integration phases. | Major | Possible | High | Order early, maintain supplier alternatives. |  |  |  | Project Controller/Managers
6 | Too much time spent researching | Reduced time available for implementation. | Moderate | Possible | High | Set research deadlines and track progress. |  |  |  | Project Controller/Managers
7 | Too much time spent doing documentation | Insufficient time for testing and design work. | Minor | Possible | Moderate | Allocate dedicated documentation sessions. |  |  |  | Project Controller/Managers
8 | Duplication of work - having multiple team members working on one thing | Inefficient use of resources; delays in other tasks. | Minor | Likely | High | Assign clear responsibilities and track tasks. |  |  |  | Project Controller/Managers
9 | Delays in PCB fabrication or component delivery. | Shortened testing period; potential for missed milestones. | Major | Possible | High | Use express shipping and have backup suppliers. |  |  |  | Project Controller/Managers
Project Cost
10 | Delays in component procurement due to supply chain issues within $500 budget. Results in finding equipment locally which is alot more expensive. | Need to source locally at higher cost. | Moderate | Possible | High | Pre-order critical parts, keep cost buffer. |  |  |  | Project Administrator
11 | Exceeding $500 budget due to need for spare parts or redesign. | Budget overrun affecting other project areas. | Major | Possible | High | Strict budget tracking and approval process. |  |  |  | Project Administrator
12 | Budget overrun due to replacement of failed components or redesign. | Reduced funds for testing or documentation. | Moderate | Possible | High | Test components early, stress testing. |  |  |  | Project Administrator
Project Stakeholders
13 | Misalignment between team output and project partner expectations. | Late-stage rework required; delays and reduced quality. | Major | Likely | Extreme | Regular partner meetings and design reviews. |  |  |  | Client Liason Manager
Safety in Design
14 | Laser output exceeding Class 1M safety limit. | Potential eye injury to users or observers. | Catastrophic | Unlikely | High | Test laser output, add safety interlocks. |  |  |  | Project Administrator
Other

## Likelihood
Criteria should be read as 'either/or'
Level | Description | Criteria
A | Always/Certain | The impact will occur
The impact occurs in all circumstances
The impact occurs daily
B | Likely | The impact is expected to occur
The impact will occur in most circumstances
The impact occurs weekly/monthly
C | Possible | The impact will probably occur
The impact has occurred before
The impact will occur under some circumstances
The impact occurs annually
D | Unlikely | The impact could occur at some time
The impact has happened elsewhere (possibly recently)
The impact occurs every 10 years or so
E | Rare | The impact may occur in very exceptional circumstances
A similar incident has occurred elsewhere
Almost impossible

## Risk Matrix
Consequence
| 1 | 2 | 3 | 4 | 5
Likelihood | Insignificant | Minor | Moderate | Major | Catastrophic
Always | H | H | E | E | E
Likely | M | H | H | E | E
Possible | L | M | H | E | E
Unlikely | L | L | M | H | H
Rare | L | L | M | M | H
Risk Level | Priority | Example Action
Extreme | 1 | Cease activity or task; detailed research and planning required.
High | 2 | Senior management attention; immediate corrective and preventative action required
Moderate | 3 | Management responsibility assigned; corrective and preventative action plan developed
Low | 4 | Manage by routine procedures; accept risk

## Hierarchy of controls
least effective
most effective

## Top 5 Risks (hidden)
Description | Risk | Mitigation
Unclear Initial Scope and Evolving Requirements | The initial project brief contained several ambiguities regarding performance expectations, interface design, and hardware limitations. As development progressed, challenges to requirements emerged, increasing the risk of delivering outcomes misaligned with client needs and the approved specification. Without clear definition, this could have led to unnecessary rework, delays, or non-compliance with stakeholder expectations. | The team mitigated this risk through structured Technical Query (TQ) submissions, which were used to clarify uncertainties and confirm design directions. Access to other teams’ submitted TQs working on the same project provided additional context and helped identify common challenges early, reducing duplication of effort. Weekly client liaison meetings were held to verify evolving requirements, while a formal change control process ensured all scope updates were reviewed, approved, and documented. All modifications were recorded in a shared repository to maintain full traceability between client communication, TQ responses, and design outcomes.
Final PCB Design Not Meeting Performance Requirements (Latency, Transfer Rate) | There was a risk that the MCU and supporting PCB design might fail to achieve the required communication speed and latency specifications during testing and final demonstration. Potential causes included hardware limitations in the chosen microcontroller, PCB trace impedance affecting signal integrity, or inefficiencies in the serial communication protocol. These issues could have resulted in unstable data transfer, increased latency, or inconsistent signal timing, compromising the project’s ability to meet stakeholder expectations for a real-time optical link. | The team mitigated this by conducting early-stage prototype testing to characterise data throughput and latency under controlled conditions. Results from these tests informed design refinements before final PCB fabrication. Extensive firmware optimisation was performed to streamline serial communication routines and minimise processing delay between transmit and receive cycles. Performance benchmarking was repeated after each design iteration to confirm incremental improvements. Furthermore, hardware alternatives (such as different MCU clock configurations and buffer sizes) were evaluated to ensure sufficient bandwidth. Final verification testing was completed under real operating conditions to validate that the PCB and firmware met latency and transfer rate requirements.
Delays in Component Procurement and PCB Fabrication | Component shortages and extended fabrication lead times posed a significant risk to both the project schedule and overall cost, especially under the strict $500 budget limit. Many electronic components required international sourcing, introducing uncertainty in delivery times and potential customs delays. PCB fabrication was also subject to manufacturer queue times, increasing the risk of missing critical integration milestones. Any delay in component arrival or board assembly could have caused a cascading effect on testing, debugging, and final system verification. | To minimise these risks, the team identified all critical-path components early in the design phase and submitted pre-orders well before integration deadlines. Multiple supplier and fabrication options (including local and overseas manufacturers) were evaluated to provide redundancy in case of stock shortages or shipping disruptions. Where feasible, express manufacturing and shipping services were used for time-sensitive items, particularly PCBs and optical components. A spare budget margin was reserved to accommodate expedited orders or minor price variations. Additionally, the team monitored supplier stock levels and lead times weekly, allowing proactive adjustments to procurement plans. This strategic approach ensured that fabrication and component sourcing stayed on schedule without compromising cost targets.
Exceeding $500 Budget Limit | Budget overrun due to spare parts, redesign, or replacement of failed components could impact project finances and delivery timelines. This was further complicated by supplier minimum order quantities (MOQs), which often required purchasing more components than needed for a single prototype. The constraint increased the likelihood of exceeding the allocated budget, particularly for custom PCBs, specialty ICs, and optical components with limited local availability. | A strict budget tracking and approval process was maintained throughout the project, ensuring all purchases were reviewed before commitment. The team mitigated supplier MOQ constraints by pooling component orders with other groups undertaking similar projects and sourcing from vendors offering sample quantities where possible. Early component testing and verification reduced the need for costly reorders, while alternative suppliers and local distributors were identified to minimise lead times and import costs. The project remained within the $500 allocation through careful prioritisation of essential components and efficient stock management.
Laser Output Exceeding Safety Limits | The optical transmitter risked exceeding Class 1M eye-safety thresholds, potentially causing user harm or leading to non-compliance with AS/NZS IEC 60825 standards. During development, the use of high-intensity 650 nm and 850 nm laser diodes presented a hazard if output power or beam divergence was not properly controlled. Misalignment of the laser optics or firmware malfunction could result in excessive irradiance at the receiver end, creating occupational safety concerns during laboratory testing and demonstration. | The team implemented multiple safety and compliance measures. Laser testing was performed in a controlled laboratory environment using calibrated optical power meters to verify that the emitted intensity remained within Class 1M limits. A current-limiting circuit was integrated into the driver board to prevent accidental over-driving of the diode, while an interlock switch disabled laser emission when the enclosure was open. Additional warning labelling and safety signage were applied in accordance with UWA safety guidelines. All safety measures were verified through documented testing and supervisor review, ensuring the system operated safely and remained compliant throughout all demonstration stages.